## Sheet1
Milestone 3: Gantt Chart
Legend: |  |  | Plan Duration |  |  | Actual Start |  |  | % Complete |  |  | Actual (Beyond Plan) |  | % Complete beyond plan
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE
[6 empty] | 2020-04-26 | 27 | 28 | 29 | 30 | 2020-05-01 | 2 | 3
Basic HTML for Login/Logout, Meetings, Settings | 2020-04-26 | 2 | 2020-04-26 | 2 | 100%
Create Meetings Page to view list of appointments | 2020-04-27 | 3
Connect appointment info to database | 2020-04-27 | 3
Settings: allow user to delete account | 2020-04-27 | 3
Allow creator to select availability (single range) | 2020-04-27 | 3
Make options for 15, 30, 60 minute slots | 2020-04-27 | 3
Select whether to have email confirmation | 2020-04-27 | 3
Guest: be able to view calendar at url/username | 2020-04-30 | 2
After selecting a date, be able to view available times | 2020-04-30 | 2
Sphinx documentation | 2020-05-02 | 1