## Sheet1
Milestone 2: Gantt Chart
Legend: | [6 empty] | Plan Duration |  |  | Actual Start |  |  | % Complete | Actual (Beyond Plan) | % Complete beyond plan
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE
[6 empty] | 2020-04-13 | 14 | 15 | 16 | 17 | 18 | 19
Home Page | 2020-04-14 | 2 | 14 | bar: 14 to 15
Log into an account | 15 | 1 | 15 | 1 | 100% | bar: 15
Keep the user logged in | 15 | 3 | 17 | 1 | 100% | bar: 15 to 17
Allow the user to log out | 15 | 3 | 17 | 1 | 100% | bar: 15 to 17
Create page for account creation | 14 | 1 | 14 | bar: 14
Be able to create account and add into database | 15 | 3 | bar: 15 to 17
Create a README | 14 | 2 | 14 | bar: 14 to 15
Create Sphinx documentation | 18 | 1 | bar: 18